## Environment and Culture
HREiR Action plan template 2020-22
Details
| Institution name: | Heriot-Watt University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 1 | Audience | # | Comments
| Date of submission: | 2020-09-25 | Research staff | 199 | Research Associates and Research Fellows
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Old Concordat principle and clause
Environment and Culture
Institutions must:
| Ensure that all relevant staff are aware of the Concordat | Signpost staff to access Concordat information information on HWU website | Target 10% pa increase on hits to Concordat and HR EiR webpages. | 2022-08-01 | RED/RFA |  |  | New
|  |  | Target 50% agree for CEDARS 2021 Survey question relating to awareness of Concordat. | 2021-07-01 | RED/RFA
|  | * Signpost staff to access Concordat information information on HWU intranet | Target 10% pa increase on hits to Concordat and HR EiR intranet pages. | 2022-08-01 | RED/RFA
|  |  | Target 50% agree for CEDARS 2021 Survey question relating to awareness of Concordat. | 2021-07-01 | RED/RFA
|  | * Communicate with all RA/ECRs to inform them of responsibilities | Target 50% agree for CEDARS 2021 Survey question relating to awareness of Concordat. | 2021-07-01 | RED/RFA
|  | * Update DoRs through meetings and direct communication to inform them of Manager and researcher responsbilities | Target 50% agree for CEDARS 2021 Survey question relating to awareness of Concordat. | 2021-07-01 | RED/RFA
|  | Run an annual consultation session with researchers to review progress and refine actions | Target participation rate of 50% from RA/ECR community for this event annually | 2021-07-01 | RED/RFA
|  |  | Target 50% agree for CEDARS 2021 Survey question relating to awareness of Concordat. | 2021-07-01 | RED/RFA
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | The University's Equality, Diversity and Inclusion Strategy is well established. All staff have access to the same benefits package (redundancy/redeployment policies, pensions, cycle to work, childcare, holidays, discounts etc.), and there is no differentiation for fixed term contractors. All policy reviews are subject to Equality Impact Assessements as part of the approval process. In addition there is a Policy review group including TU representation in place to consult on Policy development and review. | Annual check of policy group notes. | Sep 21 and 22 | HR |  |  | P2.1
|  |  | Target of 0 appeals against initial outcomes of discrimination grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | HR |  |  | P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | Wellbeing Strategy developed. Reporting tool introduced as additional means of raising bullying and harrassment concerns. Establish Respect amabassadors network. Grievance policy well established. HR Case monitoring. Sickness absence monitoring in place. Specific question set included in annual staff survey. 2020 Lockdown Pulse surveys outcomes related to health and wellbeing actions identified and implemented. | Establish baseline of relevant cases and improved systems for monitoring and tracking. (Review reporting tool and Ambassador network at Sep 21 and build actions for Sep 22) | Sep 21 and 22 | HR |  |  | P6.9
|  |  | Sickness absence related to mental health lower than sector benchmark. | Aug 21 and 22 | HR
|  |  | Staff Survey 2020 and 2021 wellbeing linked to workload improved by 10% pa | Dec 20 and 21 | HR/UE
|  |  | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | HR/UE
|  |  | Decrease towards target of 0 for Bullying and Harrassment responses in Staff survey 2020 and 21. | Dec 20 and 22 | HR/UE
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | * EDI (DISC Inclusion Matters) training roll out. University Executive in late Q4 2020 and roll out to reseearch managers and leader in 2021. | 80% of research managers and leaders trained by 2022. | 2022-08-01 | DISC project |  |  | P2.3
|  | All staff undertake EDI training. | Monitor EDI training annually Target 80% | Sep 21 and 22 | HR
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | * New data ethics training introduced in 2020 | Target of 80% staff attending Data Ethics training by 2022 | 2022-08-01 | RED/RFA/DoRs/Research managers |  |  | P6.1
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | * Project established to explore Research Culture at HWU with subsequent action plan to follow data and opinion gathering stage. | * Project established to explore Research Culture at HWU with subsequent action plan to follow data and opinion gathering stage. | * Project established to explore Research Culture at HWU with subsequent action plan to follow data and opinion gathering stage. | * Project established to explore Research Culture at HWU with subsequent action plan to follow data and opinion gathering stage. |  |  | P6.10
|  | Retention of Athena SWAN accreditation at School and Institutional level | Bronze awards retained or improved by 2021 | 2021-09-01 | HR/UE |  |  | P7.5
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | NA | [5 empty] | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | NA | [5 empty] | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | NA | [5 empty] | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | Participate in mandatory training for EDI. | Monitor participation levels. Target 80% | Sep 21 and 22 | HR/DoRs/Research Managers |  |  | New
|  | Implement learning from EDI training in management practices | Target of 0 for Bullying and Harrassment responses in Staff surveys | Dec 20 and 21 | HR/DoRs/Research Managers
|  | * All UE DISC training 2020 and roll out to all research managers and leaders in 2021. | 80% of research managers and leaders trained by 2022. | Sep 21 and 22 | DISC project/UE/DoRs/Research Managers
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | * Participation in Data Ethics training | 80% of research staff undertaken research ethics training by 2022. | Sep 21 and 22 | RED (RFA) /DoRs/Research Managers |  |  | New
|  | * Implement learning from Data Ethics training | Target of 0 complaints relating to research ethics. | Sep 21 and 22 | Research Managers/RED
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | Undertake training and participate in PDR Discussions. Maintain awareness of wellbeing strategy, related policies/guidance and support mechanisms available. Eg Role of the Manager, Mental Health Awareness , Respect programme and Supporting our Researchers training and resources. | Target of 80% of staff participating in PDR in line with commitment in strategy 2025 implementation plan. | Sep 21 and 22 | HR/DoRs/Research Managers |  |  | P6.9
|  | Implement learning from Training and development programmes | Target of 0 for Bullying and Harrassment responses in Staff Survey. | Dec 20 and 21 | HR//Research Managers
|  |  | Monitor sickness absence rates for RA/ECRs below sector benchmark. | Sep 21 and 22 | HR
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | Maintain awareness of Flexible working policies. | Monitor no of flexible working requests received/agreed. (RA/ECRs and HWU wide) | Sep 20 and 21 | HR/DoRs/Research Managers |  |  | New
|  | Implement flexible working and other family friendly policies as appropriate to support researchers | Staff Survey 2020 and 2021 Workload and work/life balance questions for Staff Survey improved by 10% pa. | Dec 20 and 21 | HR/DoRs/Rsearch Managers
|  |  | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 20 and 21 | HR/DoRs/Research Managers
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Participation in Wellcome Trust Survey action planning response. Participation in Policy Development Group. Participation in Athena SWAN Action groups. | Report representation from all research staff groups participating in policy development activities and working groups. Monitor via annual reporting to UCRI from Heads of School, DoRs and Heads of Institute. | Sep 21 and 22 | RED (PSI) /DoRs |  |  | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | Membership of Research Staff and Postdoc Forums. Participation in Athena SWAN and other School based working groups and commitees. | Monitor representation at School level of research staff groups participating in activities. Report annually to UCRI. | Sep 21 and 22 | UCRI/Researchers |  |  | New
|  | Participation in local, School and HWU inductions. | Monitor at School and Institute level. Report annually to UCRI | Sep 21 and 22 | HR/UCRI/Researchers
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | Participate in mandatory training for research integrity and EDI. Include in PDR discussions | Target of 80% of research staff undertaken research ethics training by 2022. | Sep 21 and 22 | HR/Researchers |  |  | P5.3
|  |  | Target of 80% staff undertaken EDI training by 2022 | Sep 21 and 22 | HR/Researchers
|  | Implement learning from research integrity and EDI training | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | Researchers
ECR3 | Take positive action towards maintaining their wellbeing and mental health | * Maintain awareness of wellbeing policies and resources. | Sickness absence related to mental health and wellbeing linked to workload lower than sector benchmark. | Aug 21 and 22 | HR/Researchers |  |  | New
|  | * Implement learning from wellbeing and mental health resources eg accessing services when needed | CEDARS 2021 above national average and Staff Survey 2020 and 2021 Wellbeing and work life balance questions improved by 10% pa. | 2021-07-01 | Researchers
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | Established measures including formal line management, Research Staff reps, TUs and confidential reporting app | Establish baseline for CEDARS Environment and Culture questions relating to reporting against these standards | 2021-07-01 | Researchers |  |  | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Undertake opportunities for participation in School and HWU committees and Research Culture related events eg Festival of Research, Research Culture Grant bids etc | Ensure representation from all research staff groups participating activities. Monitor via annual reporting to UCRI from Heads of School, DoRs and Heads of Institute. Evidence through PDR discussions. | Sep 21 and 22 | Researchers |  |  | P3.13?
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional suport staff; technicians.

## Employment
HREiR Action plan template 2020-22
Details
| Institution name: | Heriot-Watt University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 1 | Audience | # | Comments
| Date of submission: | 2020-09-25 | Research staff | 199 | Research Associates and Research Fellows
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Old Concordat principle and clause
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | All adverts, jd's and personal specs meet requirements. Disability confident employer. Armed Forces Covenant. Recruitment training. Policies and practices subject to Equality Impact Assessments. Move to fully centralised recruitment processes. | Monitor applications process stats - gender, ethnicity and disability. Ensure in line with wider HWU and sector demographics. | Sep 21 and 22 | HR |  |  | P1.2
P6.2
|  |  | CEDARS survey response to recruitment process above national average and improve by 10%. | 2021-07-01 | RED (RFA) |  |  | P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | Local, School and HWU inductions in place. New guidance in place for RA/ECRs. | Ensure data for RA/ECR participation in line with HWU wide participation. | Sep 20 and 21 | HR |  |  | p3.6
|  |  | Target of above national average and 10% increase for CEDARS survey response to participation in inductions. | 2021-07-01 | RED (RFA)
|  |  | Target of above national average and 10% improvement for CEDARS survey response to usefulness of inductions | 2021-07-01 | RED (RFA)
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | Career progression processes subject to Equality Impact Assessments. | Target of above national average and 10% improvement for CEDARS survey results 2021 for Career progression. | 2021-07-01 | RED (RFA) |  |  | P2.6
P6.3
P6.4
|  |  | Staff Survey results for career progression for RA's in line with other staff groups. | Dec 20 and 21 | HR
|  |  | Monitor success rate for career progression applications for RAs to esnure this is in line with wider HWU rates. | Sep 21 and 22 | HR
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | * Supporting our Researchers programme introduced in 2019/20. Role of the Manager training and resources relaunched in 2020. | Target of above national average and 10% improvement for CEDARs questions related to line management | 2021-07-01 | RED (RFA) |  |  | P6.7
|  |  | Staff Survey results relating to line managers increase by 10% pa | Dec 20 and 21 | HR
|  |  | Identify research manager staff group and target 50% research managers participating in Supporting Our Researchers programme by 2022. | 2022-09-01 | RED (RFA) |  |  | P2.3
|  |  | Increase use of 'Role of the Manager' programme resources - 10% pa increase in intranet hits. | Sep 21 and 22 | HR
|  |  | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | HR/UE
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | * 'Role of the Manager' programme relaunched. PDR revised. | Participation in PDR Target 80% in line with commitment in strategy 2025 implementation plan. | Oct 20 and 21 | HR |  |  | P2.6
|  | * 'Supporting our Researchers' programme includes 'Managing your Research Group' to support people management development | Target of above national average and 10% improvement for CEDARS for line manager questions | 2021-07-01 | RED (RFA) |  |  | P6.3
|  | * Quarterly Policy Update for research managers | Staff Survey results for career progression and workload for RA's in line with other staff groups. | Dec 20 and 21 | HR |  |  | P6.4
|  |  | Monitor success rate for career progression applications for RAs to ensure this is in line with wider HWU rates. | Sep 21 and 22 | HR
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | * Project to explore move to 'open ended with funding end date' contracts for all contracts beyond 18 months for research staff. Complete by June 2021 | Scope of project and implementation plan in place. | 2021-06-01 | HR |  |  | P1.3
|  |  | All eligible staff to move to open ended contracts by 2022 (Where funding available and time to end of contract appropriate) | 2022-09-01 | HR |  |  | P2.1
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | Membership and representation on School and HWU conmmittees eg Athena SWAN, School Management, RSF, Short life working groups etc | Ensure representation from all research staff groups participating in activities. Monitor via annual reporting to UCRI from Heads of School, DoRs and Heads of Institute. | Sep 21 and 22 | UCRI |  |  | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | NA | [5 empty] | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | NA | [5 empty] | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | NA | [5 empty] | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | NA | [5 empty] | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | Participate in PDR Reviewer training. Participate in Supporting our Researchers training. Access Role of the Manager resources. Undertake mandatory trianing eg EDI, H&S etc | Target of above national average and 10% improvement for CEDARS survey results relating to line management | 2021-07-01 | HR/RED (RFA) /DoRs/Research Managers |  |  | P2.3
|  | Implement learning from Training and development programmes | Staff Survey results relating to line managers increase by 10%. | Dec 20 and 21 | HR/Research Managers
|  |  | Target 50% research manager participating in Suporting Our Researchers programme by 2022. | Sep 21 and 22 | RED (RFA)/Research Managers
|  |  | Increase use of Role of the Manager resources - 10% pa increase in intranet hits. | Sep 21 and 22 | HR/Research Managers
|  |  | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | HR/DoRs/Research Managers
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | * Participate in training and development eg Supporting our Researchers' Managing Your Research Group' | Participation rates 50% | Sep 21 and 22 | RED (RFA) /DoRs / Research Managers |  |  | P2.2
|  | * Implement learning from 'Supporting our Researchers' programme and 'Managing Your Research' Group | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | HR/ Research Managers
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Participate in Recruitment, EDI, PDR and other mandatory training. Undertake and record PDRs in line with HWU requirements. | Participation in PDR Target 80% in line with commitment in strategy 2025 implementation plan. | Sep 20 and 21 | HR/DoRs/Research Managers |  |  | P6.3
|  | Implementation of learning from development | Target of above national average and 10% improvement for CEDARS survey results for Inclusion questions. | 2021-07-01 | DoRs and Research Managers (RFA to monitor)
|  |  | Staff Survey results for career progression and workload for RA's in line with other staff groups. | Dec 20 and 21 | HR/DoRs/Research Managers
|  |  | Monitor success rate for career progression applications for RA/ECRs to ensure this is in line with wider HWU rates. | Sep 21 and 22 | HR
EM4 | Actively engage in regular constructive performance management with their researchers | Undertake and record PDRs in line with HWU requirements. | Participation in PDR Target 80% in line with commitment in strategy 2025 implementation plan. | Oct 20 and 21 | HR/DoRs/Research Managers |  |  | P2.3
|  |  | Target of above national average and 10% improvement for CEDARS survey results for Career progression and Inclusion questions. | 2021-07-01 | Research Managers (RED (RFA) to Monitor)
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | UCRI Membership. School and other HWU wide committees. Policy Group membership | Ensure representation from all research staff groups participating in activities. Monitor via annual reporting to UCRI from Heads of School, DoRs and Heads of Institute. | Sep 21 and 22 | Research Managers /UCRI |  |  | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | * Ensure that they work in accordance with their employment contract. | Target of 0 appeals against initial outcomes of related grievances/complaints. (Aim to encourage proper reporting and process but move towards 0 complaints) | Sep 21 and 22 | HR/DoRs/Researchers |  |  | New
ER2 | Understand their reporting obligations and responsibilities | * Ensure that they comply with reporting Eg Reporting sickness absence, annual leave, completing PDR and mandatory training etc | Monitored through line manager relationship eg PDR and 1-1 meetings. | Annually and Ongoing | HR/Researchers |  |  | New
ER3 | Positively engage with performance management discussions and reviews with their managers | Undertake and record PDRs in line with HWU requirements. | Participation in PDR Target 80% in line with commitment in strategy 2025 implementation plan. | Oct 20 and 21 | HR/Researchers |  |  | P5.6
|  |  | Target of above national average and 10% improvement for CEDARS survey results for Career progression and Inclusion questions. | 2021-07-01 | Researchers /(RFA to monitor)
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | Research Staff Forum and PostdocForum. Contribution to Research Culture eg participation in Festival of Research as speakers and event attendees. Membership of Global Employee Experience Forum. Participation in CEDARS and Staff Surveys | Ensure representation from all research staff groups participating in activities. Monitor via annual reporting to UCRI from Heads of School, DoRs and Heads of Institute. CEDARS and Staff Survey participation rate 2021 Target 50% | Sep 21 and 22 | Researchers/UCRI |  |  | P5.2

## Professional and Career Develop
HREiR Action plan template 2020-22
Details
| Institution name: | Heriot-Watt University | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 1 | Audience | # | Comments
| Date of submission: | 2020-09-25 | Research staff | 199 | Research Associates and Research Fellows
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Old Concordat principle and clause
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | Offer range of development opportunities including RFA workshops, Enterprise initiatives eg Converge Challenge, Professional and Organisational Development programmes, mandatory training, Festival of Research, School based training, participation in Forums and committees, L&T programmes(LEADS and PGCAP), encouragement to participate externally across networks and conferences. | Target engagement of 50% of RA/ECRs community in development programmes. | Sep 21 and 22 | Training providers across HWU (Monitored by RED (RFA)) |  |  | P3.1
|  | * Communicate target to all RA/ECRs relating to the 10 day development expectation and raise awareness within RA/ECR community of range of development opportunities and expectations (what constitutes development). | CEDARS survey 2021 response on development time and opportunities target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) |  |  | P3.3
P5.5
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | PDR Reviewer Training | PDR participation rate 80% in line with commitment in strategy 2025 implementation plan. | Oct 20 and 21 | HR |  |  | P3.10
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | Career management programmes in place eg Careers within and beyond academia | Target of above national average and 10% improvement for CEDARS Survey results on career management questions. | 2021-07-01 | RED (RFA) |  |  | P3.1
|  | * Undertake review of career origins for new starters and destinations for leavers. | Outcome of review submitted to UCRI and University Executive in 2021. | 2021-09-01 | HR
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | * Linked to PCD11 above and through visibility at international research conferences, joint authoring of research papers and co-supervising of PhD students | Target for all eligible staff to publish one paper and attend one conference every 3 years. Track in annual research performance review | Sep 21 and 22 | Planning office |  |  | P3.11
P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | Career management programmes in place. | Target of above national average and 10% improvement for CEDARS Survey results on career management questions. | 2021-07-01 | RED (RFA) |  |  | P3.2
|  | * Undertake review of career origins for new starters and destinations for leavers. | Outcome of review submitted to UCRI in 2021. | 2021-09-01 | HR |  |  | P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | Monitor participation levels each semester with development programmes at programme level and report to UCRI (via RSF) (Use new ERP system to monitor once this is in place) | Target of 50% of RA/ECR community to engage with professional development annually | Sep 21 and 22 | RED (RFA)/UCRI |  |  | New
|  | Gather feedback on programme basis and via research staff representatives and DoRs and evaluate annually with report to UCRI outlining proposed improvements | CEDARS survey 2021 response on development time and opportunities target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA)
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | NA | [5 empty] | P3.7
P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | NA | [5 empty] | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | NA | [5 empty] | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Undertake and record PDRs in line with HWU requirements. (Establish personal development planning discussions as an integral part of HWU's research culture) | Participation in PDR Target 80% in line with commitment in strategy 2025 implementation plan. | Oct 20 and 21 | HR/DoRs/ Research Managers |  |  | P2.3
|  | Support researchers to identify appropriate career development plans | Target of above national average and 10% improvement for CEDARS survey results 2021 for Career development questions. | 2021-07-01 | RED (RFA) /DoRs/Research Managers
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | Line management responsibility for providing advice and signposting to apropriate careers support including career planning development, coaching, secondments and access to mentors where appropriate. | Target of above national average and 10% increase in response to CEDARS survey results 2021 for Career options and progression questions. | 2021-07-01 | HR/DoRs/ Research Managers |  |  | P3.4
P3.8
P5.5
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | * Communicate target to all RA/ECRs relating to the 10 day development expectation. | CEDARS survey 2021 response on development time and opportunties target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) /DoRs/Research Managers |  |  | New
|  | * Incorporate commitment to development and costs where appropriate into Grant funding bids. | Monitor bids and awards on quarterly basis and report annually to UCRI. | Sep 21 and 22 | RED (RFA) /DoRs/Research Managers
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | Offer range of development opportunities including RFA workshops, Enterprise initiatives eg Converge Challenge, Professional and Organisational Development programmes, mandatory training, Festival of Research, School based training ( examples), participation in Forums and committees, L&T programmes(LEADS and PGCAP), encouragement to participate externally across networks and conferences. Communicate target to all RA/ECRs relating to the 10 day development expectation. | CEDARS survey 2021 response on development time and opportunities target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) /DoRs/Research Managers |  |  | P3.6
|  | Raise awareness within RA/ECRs community of range of development opportunities and expectations (what constitutes development). | Monitor engagement with development programmes and ensure these are in line with wider HWU research/academic staff rates. | Sep 21 and 22 | RED (RFA) /Other training providers) / DoRs |  |  | P3.9
P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | Participation in leadership and management programmes for PIs and Research Leaders eg Supporting our Researchers, Crucible, POD Leadership programmes | CEDARS survey 2021 response to questions on leadership development target 50%. | 2021-07-01 | RED (RFA) /Other training providers / DoRs/Research Managers |  |  | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Develop PDP and Career Planning. Identify development needs through PDR process. | CEDARS survey 2021 response on development time and opportunties target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) / Researchers |  |  | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | Participation in range of development opportunities including RFA workshops, Enterprise initiatives eg Converge Challenge, Professional and Organisational Development programmes, mandatory training, Festival of Research, School based training (eg - seminar series), participation in Forums and committees, L&T programmes(LEADS and PGCAP), encouragement to participate externally across networks and conferences. | CEDARS survey 2021 response on development time and opportunities target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) /Other training providers / Researchers |  |  | P3.8
|  |  | Monitor engagement with development programmes and ensure these are in line with wider HWU research/academic staff rates. | Sep 21 and 22 | RED (RFA)
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | Take responsibility for recording and reflecting on PDP and Career Planning. Discuss as part of PDR process. | CEDARS survey 2021 response on development time and opportunties target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) / Researchers |  |  | P5.5
PCDR4 | Positively engage in career development reviews with their managers | Undertake and record PDRs in line with HWU requirements. (Establish personal development planning discussions as an integral part of HWU's research culture) | Participation in PDR target 80% in line with commitment in strategy 2025 implementation plan. | Oct 20 and 21 | HR / Researchers |  |  | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Proactively identify and suggest opportunties such as conference attendance, paper authorship, visits to other research laboratories etc. Participation in range of development opportunities including RFA workshops, Enterprise initiatives eg Converge Challenge, Professional and Organisational Development programmes, mandatory training, Festival of Research, School based training ( examples), participation in Forums and committees, L&T programmes(LEADS and PGCAP), encouragement to participate externally across networks and conferences. | CEDARS survey 2021 response on development time and opportunties target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) /Other training providers / Researchers |  |  | P5.5
|  |  | Target above national average and 10% pa increase in CEDARS Survey results on career management questions. | 2021-07-01 | RED (RFA) / Researchers
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | Actively engage with University level opportunities relating to PE via HWEngage and entrpreneurial and business development activities through the Enterprise and RED teams. Engage with L&T activities where appropriate via the L&T Academy. Assist the University in responding to national policy consutations of relevance to the RA/ECR community. | CEDARS survey 2021 response on development time and opportunties target 50% of respondents achieving 10 days. | 2021-07-01 | RED (RFA) /Other training providers / Researchers |  |  | P5.2
|  |  | Target above national average and 10% increase in CEDARS Survey results on career management questions. | 2021-07-01 | RED (RFA) / Researchers
|  |  | Monitor engagement with relevant development programmes and ensure these are in line with wider HWU research/academic staff rates. | Sep 21 and 22 | RED (RFA)

## Key
ALD | Centre for Academic Leadership and Development | Now Research Futures Academy - Division within the Research Engagement Directorate
CEDARS | Culture Employment and Development in Academic Research Survey
CROS | Careers inreserach Operational Survey
DISC | Disability Inclusive science Careers project
DoR | Director of Research
DP | Deputy Principal
ED&I | Equality, Diversity and Inclusion agenda
ERP | Enterprise Resource Planning System | Integrated business processes system - replacement for iHR
H&S | Health and Safety
HR/HRS | Human Resources Operational team | Division of the Human Resources Directorate
HERA | Higher Education Role Analysis
HRD | Human Resources Directorate
HWU | Heriot-Watt University
iHR | HR information system
IS | Information Services Directorate
JD | Job description
KE | Knowledge Exchange
L&T | Learning and Teaching
LEADS | Learning Enhancement and Development Skills programme
OD | Organisational Development | Now Professional and Organisational Development - Division of the Human Resources Directorate
PDMS | Personal Development Management System | Course and Event registration system within RFA
PDR | Performance and Development Review
PE | Public Engagement
PGCAP | Postgraduate Certificate in Academic Practice programme
PIRLS | Prinicipal Investigator
PIRLS | Principal Investigator and Research Leaders Survey
PSI | Policy Strategy and Impact Division | Division of the Research Engagement Directorate
PSLB | Professional Services Leadership Board
RA's/ECRs | Research Associates/Early Career Researchers
RED | Research Engagement Directorate
REE | Reward and Employee Engagement | Division of the Human Resources Directorate
RFA | Research Futures Academy | Division of the Research Engagement Directorate
RES | Research and Enterprise Services | Now split into RED and Enterprise Directorates
RSF | Research Staff Forum
SC | Scottish Crucible programme
UCEA | Universities and Colleges Employers Association
UCRI | University Committee for Research and Innovation
UE | University Executive
* | Denotes a new action for this period